## Project Task Due Dates
PERSON (S) | TASK (S) | Wk0 |  |  |  | Wk1 |  |  |  | Wk2 |  |  |  | Wk3 |  |  |  | Wk4 |  |  |  | Wk5
|  | March | [8 empty] | APR
|  | S17 | M18 | W20 | Th21 | S24 | M25 | W27 | Th28 | S31 | M1 | W3 | Th4 | S7 | M8 | W10 | Th11 | S14 | M15 | W17 | Th18 | S21 | M22 | W24 | Th25
All | Project Proposal
All | Data Set Search
All | Data Preprocessing, Merge, and EDA
All | Feature Engineering
All | Run Existing Models on New Data
All | Project Check In

## Full Timeline
PERSON (S) | TASK (S) | Wk0 |  |  |  | Wk1 |  |  |  | Wk2 |  |  |  | Wk3 |  |  |  | Wk4 |  |  |  | Wk5 |  |  |  | Wk6 |  |  |  | Wk7 |  |  |  | Wk8
|  | March | [8 empty] | APR | [16 empty] | MAY
|  | S17 | M18 | W20 | Th21 | S24 | M25 | W27 | Th28 | S31 | M1 | W3 | Th4 | S7 | M8 | W10 | Th11 | S14 | M15 | W17 | Th18 | S21 | M22 | W24 | Th25 | S28 | M29 | W1 | Th2 | S5 | M6 | W8 | Th9 | S12 | M13 | W15 | Th16
All | Project Proposal
All | Data Set Search
All | Data Preprocessing, Merge, and EDA
All | Feature Engineering
All | Run Existing Models on New Data
All | Project Check In
All | Hyperparameter tuning for existing models
All | New Model Creation
All | Model Comparison
All | Comparison to Open Source Project
All | Project final report and video